## Sheet1
Date	Comment	Time	Rate	Cost	days submitted
11/08/19	Meeting with Garrett at SSU, going over scope and state of project	5	35	175
11/13/19	Working trough docs available, indicating wrong revision files, prep proposal for	4	35	140
11/16/19	assembly of 5 PCBS from incomplete documentation,	4	35	140
	Proposal delivered 11-16-2019 –			0
				0
11/21/19	Downloading PCB files from Board mfg houses and puzzling out which design files go with	4	75	300
	latest builds of the boards			0
11/22/19	Commute to SSU for meeting to gather “example” and bone-pile boards for learning component	3	35	105
	values from them, so that schematic can be completed. Taking inventory of parts bin.	6	75	450
11/25/19	Battery Board – extracting comp values and correcting schematic	8	75	600
11/26/19	Linksprite Board – extracting comp values and correcting schematic	8	75	600
11/27/19	uStar Board – extracting comp values and correcting schematic	5	75	375
11/28/19	Ustar creating BOM, selecting Pns from Digikey – Looking through old orders to match up	3	75	225
11/29/19	Battery and Lightsprite – creating BOM, “”	4	75	300
11/30/19	Combining BOM parts into one Digikey order – excluding parts already on hand	2	75	150

	3560	0
12/04/19	Assemble Battery board	3	75	225
12/05/19	Assemble LightSprite-Coil brd	3	75	225
12/05/19	Assemble uStar board #1	6	75	450
				0
01/05/20	Cleaning up schematics – creating GIT repository on GitHub	4	75	300
01/29/20	Meeting with Garrett at SSU, returning parts and finished boards	6	35	210
				0
				0
				0
				0
				0
				0
				0
				0

	total			4970

06/10/20	Working up a 3D model example for Battery Board with Eagle Cad / Fusion 360	8	75
06/22/20	Looking over u-star schematic and writing down notes for redo of schematic & exporting the Libs	5	75
06/24/20	taking notes on rework of battery board	3	75
	Submitted 2 days for payment 6/24/20	0		1200		Received
		-------------------------------------------
07/02/20	conversation with Garrett about schematics and changes – Setting up Zoom meeting	2	75
07/08/20	Deciphering Battery schematic and writing circuit description for current design	5
07/09/20	Discussing Battery schematic and operation, finding faults in schematic and BOM , testing actual circuit	8.5
07/10/20	repairing smoked battery board and taking timing measurements	2
07/13/20	Setting up experiment to measure current consumption during charge up timeout	2
07/14/20	taking measurements on IC1 load lockout circuit and Pololu 5V regulator when batt totally empty	2.5
07/15/20	Sketching up new circuit for battery management and turn-on delay , discuss with Garrett	4.5
07/16/20	design OVP/UVP/Lockout battery circuit , Schematic entry	8.5
07/17/20	Layout and component selection of test circuit of OVP/UVP/Lookout	6
07/20/20	Finish layout, order parts, Ship Battery V8 board back to Garrett	7
	Submitted	-------------------------------	6	3600		Received

08/03/20	received PCB – soldered up one test board	2
08/04/20	check out circuit	8
08/05/20	discuss with Garrett – modify according the discussion and measurments – add external clk ckt	6
08/06/20	Chg bd,remove Pololu, add Bandgap reference, add 7555 for timing – change schematic	8
08/07/20	Finished re-layout , ordered PCB ,ordered parts , sent schematic to Garrett	2
08/27/20	Built Version2 of moni brd. And tested timing function / UVP function	6
08/28/20	Verified OVP function – Modified circuit to make it work/ Discussion with Garrett	8
	Submitted		5	3000

09/04/20	NICD OVP research, depopulating PCB, sending PCB, Write Circuit description of timing part	8
09/08/20	Full size battery monitor lib and layout	6
09/09/20	“”	6
09/10/20	“”	6
09/11/20	“”	8
09/14/20	“”	6
09/15/20	Ordering v09 boards from PCBway . Formatting files in Gerber fmt	4
09/16/20	Start on Ustar pcb Looking at RFM 22 and 23 radios, PCB models for RFM,9DOF, appmodule etc	8
09/17/20	uStar Schematic entry and library elements, further discussion with JGI on how to add 2 radios	10
09/25/20	uStar -SD card Eagle template, Finished Schematic – rough placement	4
09/28/20	Phone call with Garrett, discussion on how to deal with dual radios and SD card on bus lines, start layout	6
	Total , submitted 9/28/20 – incl 6hrs	72	9	5400

10/01/20	Started Layout – Discussion with G about use of Aux UART port and placement of FTDI connector, making 90 deg FTDI device template and plcement on BRD	4
10/02/20	Phonecall from G that AUX UART pinout is NOT was discussed prior – Srcap layout and placement of FTDI, Layout of 4Pin cable connector for RX,TxAnt etc. and Analog switches to radaio	4
10/05/20	Laoyout u-star	9
10/06/20	“”	6
10/07/20	“”, lib management , 50 ohm trace calc	5
10/12/20	Schematic cleanup – Order PCB – BOM – Parts Numbers	8
10/13/20	BOM – Battery board, compile make up order for 2 boards each.	4
10/14/20	Investigating MSP430 Impedance on ADC12 inputs	1.5
10/15/20	Add to DK order for Base station Radio , submit order	0.5
10/15/20	Order total $160 *1.5 for income taxes = 240 /75 = 3.2hrs	3.5
10/19/20	Finish Battery boards	2
10/20/20	Build uStar 2 pcb, recheck DK order , Some missing parts in order, conversation with Garreth	8
10/21/20	Built 4 BaseStation Radio Boards, Marked up schematics – phone call with G,	8
10/22/20	Clean up of schematic, GIT check in – cleaning up of epf files and libs	3
10/23/20	Shipping PCBs – sending zip files to Garrett	1.5
	Total submitted 10-28-20	68.5	8.5	5100

11/06/20	added assembly variant option to uStar schematic for Ground radio station	2

12/03/20	PHONE SUPPORT for Garreth	4
12/07/20	Cad modeling uStar PCB	8
12/08/20		4
12/09/20		4
12/10/20	Cad modeling battrery PCB	8
12/11/20	Excel cost spreadsheet from Digikey /ebay prices	3
12/12/20	“”	1
12/16/20	Phone support for Garreth	2
12/17/20	check in to Github – re-do of 3d lib for battery bd	2

12/18/20	Total Submitted 12/18	38	75	2850	4.75

		0
01/05/21	Create 3D cad model for App board V1.31	5
01/27/21	phone support 1-5 through 1-27	5
01/28/21	total , submitted 10hrs – corrected to 8 hrs due to overpay/ whole days only	10	75	600	1

01/29/21	Create shopping cart at Digikey – research back-order of 9DOF chip. /AA tabbed nimh	5
02/02/21	create breakout board for Bosch BMX160	5
02/04/21	Schematic prep for Coil board discussion / phone calls	5
02/05/21	Battery Board soldering – testing timing circuit again – can not duplicating Garretts Timiing problem	7
02/08/21	uSTAR BOARD SOLDERING (4)	5
2/'9/21	“”	5
02/10/21	debugging why the battery timeout gets re-triggert by the ustar brd. . 10 us pulse from Ustar after 2 sec	3
02/11/21	updated schematic/layouit/bom with changes for RC on UVP trig	2
02/11/21	Looking into the Shutoff when large Radio Transmits – can not bypass that with RC	3
02/16/21	battery drop discussion, testing different batteries, current readings v.s. Voltgage drop	2
02/17/21	sending pictures of scope traces, testing current measurement circuitry, high tx has funny load phases	3
02/18/21	building 9dof pcb , setting up test rig with Arduino 3V, testing, placing on ustar pcb	4
02/23/21	exchanging boards – fixing 1.st example ustar -radio, going over errant UVP pulse on startup again, explaining the need for turning the data lines on the radio to 0 before powering off	8
02/24/21	changing radio brd schematic/layout to disconnect radios via radio_SHDN control rather than VCC	3

02/25/21	total hours	60
	Submitted	56	75	4200	7
	left over for next month	4